## Product Backlog
Product Name: | Mav’s Animal Shelter Software (MASS) | [6 empty] | Complete Fields in Green!!!
Team ID: | Bipin Shrestha
| Team Member Name | [5 empty] | Initials | Student ID
Required | Bipin Shrestha | [5 empty] | BS | 1001841216
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 22 |  |  |  | Total | Total number of features (in column H)
1 | 18 | 4 |  |  | 1 | Total features left at the end of Sprint #1
2 | 11 | 7 |  |  | 2 | Total features left at the end of Sprint #2
3 | 6 | 5 |  |  | 3 | ...and so on
4 | 2 | 4
5 | -2 | 4
Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
ANIMAL | 1 | 1 |  | 5 | 1 | Finished in Sprint 1 | User | Track the name, gender, and age for all animals | Keep track of guests at our shelter | Need enum for Gender and abstract Animal class with constructor, getters, and toString. Validate that age is not negative else throw an exception.
DOG | 2 | 1 |  | 8 | 1 | Finished in Sprint 1 | Staff | Create a new dog (or any other family of animals) | Track pets seeking good homes | Need Dog class that extends Animal along with DogBreed enum (may be any animal family, not necessarily Dog).
LANIM | 3 | 1 |  | 8 | 1 | Finished in Sprint 1 | Staff | Keep a list of animals | See what animals are available | Requires Shelter class with a shelter name and array list of animals. Need to be able to add an animal and access the available animals.
LIZARD | 4 | 1 |  | 5 | 1 | Finished in Sprint 1 | Staff | Create and list cats (or 2nd animal family) as well | Put 2nd pet type up for adoption | Very similar to 1st type of pets
MAINWIN | 5 | 2 |  | 3 | 2 | Finished in Sprint 2 | User | Display a main window with menu | Use the program more easily | Baseline Nim
TOOLBAR | 6 | 2 |  | 2 | 2 | Finished in Sprint 2 | User | Include a toolbar | Click buttons for actions | Baseline Nim; add 2 buttons for inserting the two animal families
ABOUT | 7 | 2 |  | 3 | 2 | Finished in Sprint 2 | User | Include an About dialog for toolbar icons (Help > About) | Avoid legal trouble | Baseline Nim; need icons for the two animal families; use YOUR name
EXIT | 8 | 2 |  | 2 | 2 | Finished in Sprint 2 | User | Exit the main program (File > Quit or x window control) | Quit reliably | Baseline Nim
DOGDIALOG | 9 | 2 |  | 13 | 2 | Finished in Sprint 2 | Staff | Use dialogs to create a new dog or 1st family (Animal > New) | Track pets seeking good homes | May be a series of JOptionPane dialogs or a single unified dialog
LIZARDDIALOG | 10 | 2 |  | 8 | 2 | Finished in Sprint 2 | Staff | Use dialogs to create a new cat or 2nd family (Animal > New) | Track more pets seeking good homes | Similar to 1st
SHOWANIM | 11 | 2 |  | 5 | 2 | Finished in Sprint 2 | Staff | Display all animals in the main window (Animal > List Available) | See the beloved animals that are current guests of the shelter | Update after every Insert operation (Animal > List Available will be needed when clients are added in a later sprint). May be a label or similar widget in the data area of the main window
SAVE | 12 | 3 |  | 8 | 3 | Finished in Sprint 3 | Manager | Save the data to a default file (File > Save) | Persist our data through the years | Requires Animal.save(bw), Dog.save, Cat.save, Shelter.save; Shelter.filename with getter and setter, and Mass.onSaveClick
LOAD | 13 | 3 |  | 8 | 3 | Finished in Sprint 3 | Manager | Load the data from a default file (File > Open) | Persist our data through the years | Requires Animal.Animal(br), Dog.Dog, Cat.Cat, Shelter.Shelter and Mass.onOpenClick; dialog and logic for handling “dirty” data
NEW | 14 | 3 |  | 5 | 3 | Finished in Sprint 3 | Director | Create a new shelter (File > New) | Open additional shelters as needed | Requires Mass.onNewShelterClick
SAVEF | 15 | 3 |  | 5 | 3 | Finished in Sprint 3 | Director | Save the data to a specified file (File > Save As) | Backup or baseline a new shelter | Requires Mass.onSaveAsClick, Shelter.setFilename; adding JFileChooser
LOADF | 16 | 3 |  | 3 | 3 | Finished in Sprint 3 | Director | Load the data from a specified file (File > Open) | Work with multiple shelters | Requires adding JFileChooser
GENERIC | 17 | 4 |  | 13 | 4 | Finished in Sprint 4 | Staff | Refactor Add (Animal) dialogs into generic class and add at least one additional family of animals | Quickly add additional animal families to our guest list | Requires generic class for unified dialog to create new animal guests
ITER | 18 | 4 |  | 5 | 5 | In Work |  | Refactor to use iterators to access animals from Shelter | Practice iterators (well?) | Replace numAnimals and getAnimal with getAnimalIterator; update all users of those methods
CLIENT | 19 | 4 |  | 8 | 4 | Finished in Sprint 4 | Staff | Create a new client (Client > New) | Track candidate adopters | Requires Mass.onCreateClient; 1 dialog; class Client; Shelter.addClient and fields
LCLIENT | 20 | 4 |  | 5 | 4 | Finished in Sprint 4 | Client | List clients (Client > List) | See which clients are available | Requires Shelter.numClients and client; and Mass.onClientsList
ADOPT | 21 | 5 |  | 13 |  | Finished in Sprint 4 | Client | Adopt an animal (Client > Adopt Animal) | Adopt an animal! | Requires Shelter.adopted HashMap<Animal, Client>, new dialog
LADOPT | 22 | 5 |  | 8 |  | Finished in Sprint 5 | Staff | List adopted animals (Client > List Adopted and Animal > List Adopted) | See which client adopted which animal | Requires 1 dialog to select the client and 1 dialog to select the animal; Mass.onListAdoptedClick
Bonus Features
NANIM |  | 4 | TBD | 5 |  |  | Client | Create new animals and / or clients during adoption | Simplify the adoption process | Add “New Client” button to the client selection dialog; Add “New Animal” button to the animal selection dialog; add logic to integrate smoothly
PHOTO |  | 4 | TBD | 8 |  |  | Client | See photo and information about an available animal | Decide if it’s right for my family | Requires existing animal selection dialog + 1 dialog derived from Animal > New with a Gtk::Image, Mainwin::on_view_animal_click.

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2022-02-22 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-03-01
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 4
Day 1 Left | 4 | 0
Day 2 Left | 1 | 3
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 0 | 1
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | ANIMAL |  | "Created animal class with constructor","Validate age and thrown exception" | Completed Day 2
2 | DOG |  | "Created class dog that extend animal with dogbreed enum with its own constructor and tostring() | Completed Day 2
3 | LIZARD |  | "Created class Lizard that extend animal with lizardbreed enum with its own constructor and tostring() " | Completed Day 2
4 | LANIM |  | "Create shelter class","Arraylist of animal and must be able to add and access the animals" | Completed Day 5
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2022-03-01 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-03-08
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 17
Day 1 Left | 17 | 0
Day 2 Left | 17 | 0
Day 3 Left | 14 | 3
Day 4 Left | 10 | 4
Day 5 Left | 10 | 0
Day 6 Left | 10 | 0
Day 7 Left | 0 | 10
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | MAINWIN |  | Create a main window with an title | Completed Day 3
2 | MAINWIN |  | Create a menu bar with file,animal and about; and giving it observers | Completed Day 3
3 | MAINWIN |  | data label that display the available animal | Completed Day 3
4 | MAINWIN |  | create toolbar with dog and cat pic and give it observer | Completed Day 4
5 | DOGDIALOG |  | create dialog box | Completed Day 4
6 | DOGDIALOG |  | create widget in dialog box of different type | Completed Day 4
7 | DOGDIALOG |  | Use GridBagLayout and coordinate to organize the widget in different places | Completed Day 4
8 | DOGDIALOG |  | Make ok and cancel button and give it a observer | Completed Day 7
9 | DOGDIALOG |  | if ok the observer create the new animal of type Dog with the input data | Completed Day 7
10 | LIZARDDIALOG |  | create dialog box | Completed Day 7
11 | LIZARDDIALOG |  | create widget in dialog box of different type | Completed Day 7
12 | LIZARDDIALOG |  | Use GridBagLayout and coordinate to organize the widget in different places | Completed Day 7
13 | LIZARDDIALOG |  | Make ok and cancel button and give it a observer | Completed Day 7
14 | LIZARDDIALOG |  | if ok the observer create the new animal of type Dog with the input data | Completed Day 7
15 | EXIT |  | exit the program when the quit is clicked(observer to quit) | Completed Day 7
16 | ABOUT |  | Dialog box providing the information about the the verson | Completed Day 7
17 | ABOUT |  | Inducle the image used and give Credit to the creator and the websites | Completed Day 7
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2022-03-08 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-03-15
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 12
Day 1 Left | 12 | 0
Day 2 Left | 12 | 0
Day 3 Left | 12 | 0
Day 4 Left | 12 | 0
Day 5 Left | 11 | 1
Day 6 Left | 11 | 0
Day 7 Left | 0 | 11
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | SAVE |  | shelther save name and arraylist size | Completed Day 7
2 | SAVE |  | animal save name, age and gender | Completed Day 7
3 | SAVE |  | Dog save breed and Lizard save bread | Completed Day 7
4 | New |  | clear the new shelther | Completed Day 5
5 | LOAD |  | onclickopen bufferedread on Shelther, Dog, Lizard,Animal | Completed Day 7
6 | LOAD |  | Jfilechose | Completed Day 7
7 | LOAD |  | magic cookei and version | Completed Day 7
8 | LOAD |  | try and catch | Completed Day 7
9 | SAVEF |  | Mass.onSaveAsClick | Completed Day 7
10 | SAVEF |  | Shelter.setFilename | Completed Day 7
11 | SAVEF |  | adding JFileChooser | Completed Day 7
12 | LOADF |  | Requires adding JFileChooser | Completed Day 7
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2022-04-12 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-04-19
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 13
Day 1 Left | 13 | 0
Day 2 Left | 13 | 0
Day 3 Left | 13 | 0
Day 4 Left | 13 | 0
Day 5 Left | 5 | 8
Day 6 Left | 0 | 5
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | Client |  | Add arraylist to shelther | Completed Day 5
2 | Client |  | Update Jframe and add toolbar for these 3 new commands | Completed Day 5
3 | Client |  | provide active lisenter | Completed Day 5
4 | Client |  | 3 commands: New, list, list avilable | Completed Day 5
5 | Client |  | Save open | Completed Day 5
6 | Client |  | Updata display accordint to anima an client | Completed Day 5
7 | Client |  | Dialog box for name and phone | Completed Day 5
8 | Lclient |  | save and open clients in a file | Completed Day 5
9 | Lclient |  | Display the clients | Completed Day 6
10 | Generic |  | Make a generic Method | Completed Day 6
11 | Generic |  | Make a create method for animals | Completed Day 6
12 | Generic |  | Adapt the code for onnewDogClick and onNewLizardClick | Completed Day 6
13 | Generic |  | Make new animal and use the genric method to create it | Completed Day 6
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2022-04-19 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-04-26
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 7
Day 1 Left | 7 | 0
Day 2 Left | 7 | 0
Day 3 Left | 7 | 0
Day 4 Left | 7 | 0
Day 5 Left | 7 | 0
Day 6 Left | 2 | 5
Day 7 Left | 0 | 2
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | ADOPT |  | Requires Shelter.adopted HashMap<Animal, Client> | Completed Day 6
2 | ADOPT |  | new dialogs | Completed Day 6
3 | ADOPT |  | override the hascode and .equal | Completed Day 6
4 | ADOPT |  | Iterate over for dialog | Completed Day 6
5 | LADOPT |  | Requires 1 dialog to select the client | Completed Day 6
6 | LADOPT |  | and 1 dialog to select the animal; | Completed Day 7
7 | LADOPT |  | Mass.onListAdoptedClick | Completed Day 7
8 | ITER |  |  | In Work
9 | ITER |  |  | In Work
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84